## Agile Documentation
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours)
US-01 | M1-T01 | Explored LLM evaluation approaches, hallucination detection strategies, RAG design patterns, and existing frameworks such as RAGAS and TruLens | 30-Jun-2026 | 03-Jul-2026 | Soma Sekhar | Research | Completed | 7
US-03 | M1-T02 | Defined the system architecture, agent responsibilities, orchestration flow, scoring dimensions, and underlying data models | 01-Jul-2026 | 05-Jul-2026 | Soma Sekhar | System Design | Completed | 8
US-01 | M1-T03 | Built the first version of the Evaluation Input Module for submitting a question, AI response, and optional reference answer or source document | 03-Jul-2026 | 07-Jul-2026 | Soma Sekhar | Implementation | Completed | 7
US-02 | M1-T04 | Set up the Reference Knowledge Base using TruthfulQA and SQuAD datasets, including chunking, embedding generation, and vector index creation | 04-Jul-2026 | 09-Jul-2026 | Soma Sekhar | RAG Development | Completed | 12
US-02 | M1-T05 | Verified retrieval quality and finalized the Milestone 1 submission | 08-Jul-2026 | 10-Jul-2026 | Soma Sekhar | Validation | Completed | 5
US-04 | M2-T01 | Developed the Relevance Judge Agent to score how well a response addresses the question, with reasoning output | 10-Jul-2026 | 15-Jul-2026 | Soma Sekhar | Agent Development | Completed | 10
US-05 | M2-T02 | Developed the Accuracy Judge Agent to verify factual correctness against reference answers or retrieved evidence, returning a score with supporting justification | 13-Jul-2026 | 18-Jul-2026 | Soma Sekhar | Agent Development | Completed | 10
US-06 | M2-T03 | Developed the Hallucination Detection Agent to flag unsupported claims by cross-checking responses against retrieved source content | 15-Jul-2026 | 20-Jul-2026 | Soma Sekhar | Agent Development | Completed | 12
US-04 | M2-T04 | Tested all three judge agents for scoring consistency and reasoning quality across benchmark question-answer pairs | 18-Jul-2026 | 22-Jul-2026 | Soma Sekhar | Validation | Completed | 8
US-07 | M3-T01 | Developed the Completeness Judge Agent to assess whether all aspects of a question were addressed and identify omissions | 22-Jul-2026 | 26-Jul-2026 | Soma Sekhar | Agent Development | Completed | 10
US-08 | M3-T02 | Developed the Verdict Agent to aggregate all dimension scores through a weighted model and generate a consolidated quality verdict | 24-Jul-2026 | 29-Jul-2026 | Soma Sekhar | Agent Development | Completed | 10
US-09 | M3-T03 | Built the per-dimension scoring and reasoning display interface showing scores, flagged hallucinations, and overall verdict | 26-Jul-2026 | 30-Jul-2026 | Soma Sekhar | UI Development | Completed | 8
US-10 | M3-T04 | Implemented CSV-based batch evaluation allowing automatic processing of multiple question-answer pairs with aggregated results | 27-Jul-2026 | 01-Aug-2026 | Soma Sekhar | Batch Processing | Completed | 12
US-11 | M4-T01 | Built the Evaluation Scoring Dashboard with pass/fail rates, average dimension scores, hallucination frequency, and quality trend charts | 01-Aug-2026 | 06-Aug-2026 | Soma Sekhar | Dashboard | Completed | 12
US-12 | M4-T02 | Implemented structured PDF report export summarizing batch evaluation results, dimension breakdowns, and improvement recommendations | 04-Aug-2026 | 08-Aug-2026 | Soma Sekhar | Report Generation | Completed | 10
US-13 | M4-T03 | Carried out end-to-end testing of single and batch evaluation workflows, verifying agent consistency and dashboard accuracy | 07-Aug-2026 | 12-Aug-2026 | Soma Sekhar | Testing | Completed | 10
US-14 | M4-T04 | Compiled technical documentation and project report covering evaluation of multiple AI systems on the platform | 09-Aug-2026 | 14-Aug-2026 | Soma Sekhar | Documentation | Completed | 8
US-14 | M4-T05 | Finalized documentation, project report, agile artifacts, and demonstration materials | 14-Aug-2026 | 21-Aug-2026 | Soma Sekhar | Finalization | Completed | 12